Date: 21 March 2026

OMEYA Blind Site measurement / order processing and installation process: 
Prepared for Compliance with Singapore Standards, BCA Guidelines, and Industry Best Practices. Process aligns with Singapore’s SS 692:2020 (Blinds and Curtains – Safety Requirements) and industry best practices for window covering installations.

### 1. Pre-Installation: Proposal & Site Measurement

A. Blind Proposal (Blind Type: OMEYA Track-guided Vertical Blind)

- Client Consultation

  - Determine requirements: light control, privacy, aesthetics, maintenance, child safety (if applicable).

  - Recommend suitable fabric, opacity, color, and operation style (manual chain, corded, or motorized).

  - Need Nestopia to provide to SGT a few more booklets that we can provide as material samples.

  - Advise on track options (ceiling/wall-mounted) and stacking direction.

- Site Measurement Method

  - Tools Needed: Laser measure, steel tape, spirit level, notepad, camera.

  - Check Window/Frame:

    - For inside recess (inside mount):

      - Measure width at top, middle, bottom; record smallest width.

      - Measure height at left, center, right; record smallest height.

      - Check for obstructions (handles, window cranks, uneven surfaces).

      - Note recess depth to ensure track and blind stack fit.

    - For outside recess (face mount):

      - Measure desired coverage width and height.

      - Ensure adequate clearance for blind operation and stacking.

    - Check for Plumb & Level: Use spirit level to note if window/wall is uneven; adjustments may be needed for smooth operation.

  - Additional Singapore-Specific Checks:

    - Check for window gates, grilles, or safety devices that may interfere.

    - Note proximity to M&E services (e.g., AC units, lights, pipes).

    - Assess access restrictions (e.g., high-rise, need for scaffolding/PMA).

- Proposal Documentation

  - Quotation preparation with:

    - Detailed measurements and mounting type.

    - Fabric sample references.

    - Track type and control mechanism.

    - Compliance statement (if applicable): fabric fire-rating, child-safe cords, or motor safety standards.

    - Delivery ETA SG and installation timeline and warranty terms.

    - Timeline:

      - SGT sends site measurement to Nestopia China: One (1) working day after the date of site measurement.

      - Technical questions / exchanges on the design/measurements between Nestopia China and SGT: Three (3) days.

      - Quotation from Nestopia China to SGT for customer to sign off once full clarification had been done: One (1) working day.

### 2. Fabrication & Pre-Installation Check

- Order Processing (SGT and Nestopia China)

  - SGT submits PO information.

  - Nestopia confirms the lead time (typically 2–4 weeks but depending on our supplier).

  - After order had been confirmed

    - SGT obtains client’s MCST approval (Submission either by SGT or by the client): 1 to 2 weeks before expected installation date

    - Sign-off before fabrication if required.

- SGT process the PO

  - SGT issues PO to Nestopia China to process the order with the supplier/factory after the signed confirmation / verbal (with phone message) of the order by customer.

  - Nestopia China confirms the PO and reverts to SGT: One (1) day after receiving PO.

- Pre-Delivery Quality Check (Factory/Workshop)

  - Verify fabric correctness, size, and hemming.

  - Ensure track length, carrier hooks, and control mechanism are correctly assembled.

  - Test run of blind operation.

- Shipment arrangement:

  - Nestopia China arranges goods with packing that meets the respective shipping standard (sea / air depending on the cost, lead-time and as required/requested by the end customer)

  - Nestopia China arranges shipment through SGT (as SGT has daily shipment in place), with insurance and shipping bills and shipping / clearing and the local custom clearing company will inform SGT on the ETA.

  - Parts ETA Singapore and reaches SGT. SGT performs

    - Visual check on parts

    - BOM/Q check

    - Arrange with customer for installation (date and time plus to get confirmation from customer for entrance approval to site)

### 3. Installation On-Site

A. Pre-Installation Site Check

- Attire of installers:

  - Attired with OMEYA’s Tee-shirt with shoe cover and / or working gloves

- Safety Briefing (for installers):

  - Use of PPE (helmet, safety shoes if at construction site).

  - For high-rise installations, ensure window openings are secured, or use fall protection equipment if working at height.

- Re-Measure on-site before unpacking: confirm measurements match.

- Check Tools & Materials:

  - Drill, screws (stainless steel for damp areas), wall plugs, spirit level, laser level, screwdriver, step ladder.

  - Zip blinds kit: track, fabric panels, carriers, chain/cord or motor.

B. Installation Steps

- Marking & Bracket Fixing

  - Use laser/spirit level to mark bracket positions on wall/ceiling.

  - For concrete walls: drill holes, insert wall plugs, secure brackets.

  - For false ceiling or gypsum board: locate studs or use appropriate anchors.

  - Ensure brackets are level and aligned; track must be straight for smooth zip operation.

- Track Mounting

  - Fix track onto brackets.

  - For corner or bay windows, join track sections securely.

- Hanging Fabric Panels

  - Insert fabric panels into carriers, ensuring they are properly clipped and aligned.

  - Zip test: run panels along track to ensure no snagging.

- Final Fixing & Adjustments

  - Install chain/cord mechanism or motor (if motorized, test remote/switch).

  - Adjust bottom chain weight or tension if necessary.

  - Ensure smooth operation across full range.

### 4. Quality Check & Handover

A. Post-Installation Inspection

- Functional Test:

  - Operate blind fully — open, close, tilt.

  - Check for smooth movement, no fabric jamming or misalignment.

  - For motorized blinds: test multiple cycles, remote sensitivity, battery/power supply.

- Visual Inspection:

  - Fabric evenly spaced, no twisting or sagging.

  - Bottom rail level when closed.

  - No exposed screws or sharp edges.

- Safety Check:

  - Chain/cord tension safe (no loose loops if children present).

  - Brackets secure, no movement when operating.

  - For motorized: wiring tucked away, no trip hazards.

B. Documentation & Handover

- Provide:

  - Operation and care instructions (English, or multi-language if required).

  - Warranty card (covering track, mechanism, fabric).

  - Contact for service support.

- Client Demonstration:

  - Show how to operate, remove/replace fabric panels for cleaning.

  - Advise on maintenance: regular dusting, no harsh chemicals, check track for debris.

- Sign-Off:

  - Obtain customer acceptance form.

  - Note any snag items and schedule follow-up if needed.

- Filling:

  - SGT / Nestopia (PIC: Persons in charge) files all relevant and approval documents: Hard and Soft copies

### 5. Post-Installation Support

- Snagging Period: 7–14 days for minor adjustments.

- Warranty: Typically 1–2 years for parts (Blinds and motor, etc.) and workmanship. (Please specify in the Quote)

- Singapore-Specific Considerations:

  - Humidity: advise on mold/mildew prevention for fabrics.

  - HDB regulations: ensure installation does not affect window fall prevention measures.

  - Motorized blinds: ensure compliance with EMSD electrical safety standards.

Checklist Summary

- Accurate measurement (triple-check)

- Client sign-off on proposal

- Pre-installation site readiness confirmed

- Safe installation procedure followed

- Functional & visual quality check done

- Customer demonstration completed

- Documentation handed over